## Sheet1
Group Name | Team Members | March |  |  |  | April |  |  |  | May |  |  |  | June
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | Notes
WP 1: Project requirement analysis and architecture design Manager: tianren Yao
Task 1.1: Analyze enterprise user core requirements and sort out functional demand list | Liu Haopu
Task 1.2: Determine the technical stack and development specification of the whole project | Li Sihang
Task 1.3: Design the overall architecture and functional module division of the platform | Liu Haopu
Task 1.4: Design the database structure and data association logic | You Haoyang
Task 1.5: Output the prototype diagram and standardized design document of the core page | Liu Haopu
Task 1.6: Complete the review and revision of design documents and conduct internal confirmation | Li Sihang
WP 2: Database development and back-end interface construction Manager: Haopu Liu
Task 2.1: Create a database instance based on design documents, complete table structure construction and association configuration | Yao Tianren
Task 2.2: Develop user account interfaces | Li Sihang
Task 2.3: Develop core business interfaces for three modules | Yao Tianren
Task 2.4: Realize interface parameter verification, exception handling and performance optimization | Li Sihang
Task 2.5: Write interface test cases and complete unit testing | Lu Yuan
Task 2.6: Output back-end interface documents to support front-end joint debugging and verify interface availability | Li Sihang
WP 3: Front-end infrastructure and common module development Manager: Sihang Li
Task 3.1: Set up the front-end project framework. | Lu Yuan
Task 3.2: Develop reusable components. | Liu Haopu
Task 3.3: Implement front-end pages and logic for user login, registration, and authentication/authorization. | Yao Tianren
Task 3.4:Design and develop global styles and responsive layout for the platform. | Liu Haopu
Task 3.5: Perform testing and optimization of the front-end base framework. | Yao Tianren
WP 4: Front-end development and joint tuning of three core business modules Manager: Haoyang You
Task 4.1: Develop a carbon emission tracking module | Yao Tianren
Task 4.2: Develop a waste management module | Liu Haopu
Task 4.3: Develop a report generation module | Lu Yuan
Task 4.4: Complete the full-scale integration testing of the three modules with the back-end interfaces and solve data interaction issues. | Yao Tianren
Task 4.5: Optimize the interaction experien ce and page loading performance within the modules. | You Haoyang
Task 4.6: Complete the functional testing of the three modules and fix known bugs. | Liu Haopu
WP 5: Platform integration test and performance optimization Manager: Yuan Lu
Task 5.1: Integrate all developed modules to ensure the smooth end-to-end business process of the platform from login to data operation and report generation. | Liu Haopu
Task 5.2: Carry out full coverage functional testing, simulate the actual use scenarios of enterprise users, test all core functions of the three modules and general modules, and record bug and problem lists. | Liu Haopu
Task 5.3: Conduct compatibility testing, ensure the platform supports mainstream browsers (Chrome/Firefox/Edge), and adapt to the network environment of Irish remote testing to avoid access and operation failures. | Li Sihang
Task 5.4: Optimize platform performance, reduce page loading time, optimize database query speed, lower interface response delay, and improve the overall operating experience of the platform. | Yao Tianren
Task 5.5: Fix all key bugs, interaction problems and performance problems found in the test process, and re-test the modified functions to ensure that all problems are solved. | Li Sihang
Task: 5.6: Complete the deployment and testing of the platform on the designated virtual machine, verify the remote access, data storage and function operation of the platform, and output the deployment test document. | Lu Yuan
WP 6: Project documentation and final delivery Manager: Haopu Liu
Task 6.1: Collate and perfect all project development documents, including requirements, architecture design, development, testing and other full-process standardized documents | Li Sihang
Task 6.2: Compile a detailed platform us er operation manual with step-by-step guidance for testers to use all core business functions | You Haoyang
Task 6.3: Generate and sort out test-specific enterprise and employee accounts, and record complete account information | Liu Haopu
Task 6.4: Complete the official deployment of the platform on the designated virtual machine, and conduct multiple verifications to ensure stable remote access and operability for Irish testing | Li Sihang
Task 6.5: Prepare comprehensive interim and final project report materials, including platform function demonstration, technical implementation details, project management process and team collaboration explanation | Liu Haopu
Task 6.6: Complete the final project acceptance, collect test and assessment feedback, and make the final fine-tuning of the platform and documents | Yao Tianren
Deliverable
Milestone